## Sheet1
Test case
PROJECT NAME : 114498 : CRF For Ashirvad NCA Robotic Automation
Software Request ID :					Project End Date	15/12/22
Created by:			HEERA P VENU		Delay	0
Created Date:					Testing Date	13/12/2022
Reviewed By			MURUGESHAN		Time
Version					UAT Retesting
Test Engineer:			HEERA P VENU,AKHILA N U
Date	TEST CASE ID	TEST CASE NAME	TEST CASE OBJECTIVE	TEST DATA/INPUT	EXPECTED RESULT	ACTUAL RESULT	ESTIMATED TIME	ACTUAL TIME	SEVERITY	TEST STAGE	TEST STATUS	REMARKS
15/12/2022	TC_01	REPORT DOWNLOADED USING QUERY	check whether the user can able to download report using query or not		the user should able to download report using query	the user is able to download report using query	0.2	0.2	High	Initial testing	Passed	Passed
15/12/2022	TC_02	ZONE WISE REPORT	Check whether the user can able to view the color in zone wise report as per the criteria or not		the user should able to view zone wise report as per the criteria	the user is able to view zone wise report as per the criteria	0.2	0.2	High	Initial testing	Passed	Passed
15/12/2022	TC_03	REGION WISE REPORT	Check whether the user can able to view the color in region wise report as per the criteria or not		the user should able to view region wise report as per the criteria	the user is able to view region wise report as per the criteria	0.2	0.2	High	Initial testing	Passed	Passed
15/12/2022	TC_04	EXCEL REPORT-zone wise report,region wise report	Check whether the user can able to receive zone wise report and region wise repot in excel format or not		the user should able to receive zone wise report and region wise repot in excel format	the user is able to receive zone wise report and region wise repot in excel format	0.2	0.2	High	Initial testing	Passed	Passed
15/12/2022	TC_05	AREA WISE REPORT	Check whether the user can able to view the color in area wise report as per the criteria or not		the user should able to view the color in area wise report as per the criteria	the user is able to view the color in area wise report as per the criteria	0.2	0.2	High	Initial testing	Passed	Passed
15/12/2022	TC_06	BRANCH WISE REPORT	Check whether the user can able to view the color in branch wise report as per the criteria		the user should able to view the color in branch wise report as per the criteria	the user is able to view the color in branch wise report as per the criteria	0.2	0.2	High	Initial testing	Passed	Passed
15/12/2022	TC_07	MAIL-zone wise report and region wise report	Check whether the zone wise report and region wise report get automatically sent to user in a excel format or not		the zone wise report and region wise report should get automatically sent to user in a excel formt	the zone wise report and region wise report is get automatically sent to user in a excel formt	0.2	0.2	High	Initial testing	Passed	Passed
15/12/2022	TC_08	MAIL-area wise report&branch wise report	Check whether the zone wise report and region wise report get automatically sent to user in a picture format or not		the zone wise report and region wise report should get automatically sent to user in a picture format	the zone wise report and region wise report is automatically sent to user in a picture format	0.2	0.2	High	Initial testing	Passed	Passed
15/12/2022	TC_09	AREA WISE REPORT,ZONE WISE REPORT & REGION WISE REPORT	check whether the reports contains region name,fzm,nca,gold weight,pledge amount,zero nca branches,zero nca areas or not		the reports should contains region name,fzm,nca,gold weight,pledge amount,zero nca branches,zero nca areas	the reports contains region name,fzm,nca,gold weight,pledge amount,zero nca branches,zero nca areas	0.2	0.2	High	Initial testing	Passed	Passed
15/12/2022	TC_10	BRANCH WISE REPORT	check whether the reports contains br_id,branch name,area name,fzm,nca,gold weight,pledge or not		the reports should contain br_id,branch name,area name,fzm,nca,gold weight,pledge	the reports contain br_id,branch name,area name,fzm,nca,gold weight,pledge	0.2	0.2	High	Initial testing	Passed	Passed
					0.2	0.2	High	Initial testing	Passed	Passed
					0.2	0.2	High	Initial testing	Passed	Passed
					0.2	0.2	High	Initial testing	Passed	Passed
					0.2	0.2	High	Initial testing	Passed	Passed
					0.2	0.2	High	Initial testing	Passed	Passed
					0.2	0.2	High	Initial testing	Passed	Passed
					0.2	0.2	High	Initial testing	Passed	Passed
					0.2	0.2	High	Initial testing	Passed	Passed
					0.2	0.2	High	Initial testing	Passed	Passed